## Distribution Feeders Committed
Limitation and timing | Location | Committed Solution
AMR - 11kV feeder AMR2 Exceeding reliability MSS | AMR - Amamoor | AMR - Improve reliability on AMR2 - Target Commissioning Sep 2022 - Cost: $0.25 M ± 30% | 415472.87 | 2021-02-05
BGY - 11kV feeder BGY6A & BGY15A Exceeding capacity TMU | BGY - Burpengary | BGY - Establish a new 11kV feeder - Target Commissioning Jun 2023 - Cost: $2.51 M ± 30% | 885995.4083 | 2021-07-23
BHD - 11kV feeder BHD23A Exceeding reliability MSS | BHD - Burleigh Heads | BHD - Improve reliability on BHD23A - Target Commissioning Oct 2023 - Cost: $0.53 M ± 30%
BNH - 11kV feeder BNH6A Exceeding reliability MSS | BNH - Boonah | BNH - Improve reliability on BNH6A - Target Commissioning May 2023 - Cost: $0.29 M ± 30% | 415472.87 | 2021-02-05
BPN - 11kV feeder BPN3 Exceeding capacity TMU | BPN - Browns Plains | BPN - Establish 11kV feeder ties - Target Commissioning Sep 2023 - Cost: $0.87 M ± 30%
CBT - 11kV feeders CBT8A & CBT12A Exceeding capacity TMU | CBT - Caboolture | CBT - Establish a new 11kV feeder - Target Commissioning Jul 2024 - Cost: $2.10 M ± 30%
CBW - 11kV feeder CBW6 Exceeding capacity TMU | CBW - Caboolture West | CBW - Establish an 11kV feeder tie - Target Commissioning Oct 2023 - Cost: $0.85 M ± 30%
CLD - 11kV feeders CLD11, CLD18A & CLD29A Exceeding capacity TMU | CLD - Caloundra | CLD - Establish two new 11kV feeders - Target Commissioning Jun 2024 - Cost: $3.50 M ± 30% | 885995.4083 | 2021-07-23
CMY - 11kV feeder CMY4 Exceeding capacity MSS | CMY - Coominya | CMY - Install a new PMR on CMY4 - Target Commissioning May 2023 - Cost: $0.15 M ± 30% | 415472.87 | 2021-02-05
CPL - 11kV feeder CPL2A Exceeding reliability MSS | CPL - Coopers Plains | CPL - Improve reliability on CPL2A - Target Commissioning Dec 2023 - Cost: $0.25 M ± 30%
CRB - 11kV feeder CRB25A Exceeding reliability MSS | CRB - Currumbin | CRB - Improve reliability on CRB25A - Target Commissioning May 2023 - Cost: $0.48 M ± 30%
CRM - 11kV feeder CRM3A Exceeding capacity TMU | CRM - Crestmead | CRM - Establish an 11kV feeder tie - Target Commissioning Oct 2024 - Cost: $0.40 M ± 30% | 885995.4083 | 2021-07-23
CRM - 11kV feeder CRM13A Exceeding reliability MSS | CRM - Crestmead | CRM - Improve reliability on CRM13A - Target Commissioning Oct 2023 - Cost: $0.31 M ± 30%
CRM - 11kV feeder CRM16A Exceeding capacity TMU | CRM - Crestmead | WRG - Install 3xLBS to deload CRM16A - Target Commissioning Jul 2023 - Cost: $0.11 M ± 30% | 885995.4083 | 2021-07-23
ENG - 11kV feeder ENG7A Exceeding reliability MSS | ENG - Enoggera | ENG - Improve reliability on ENG7A - Target Commissioning Jul 2023 - Cost: $0.18 M ± 30%
ESK - 11kV feeder ESK3A Exceeding reliability MSS | ESK - Esk | ESK - Improve reliability on ESK3A - Target Commissioning Apr 2023 - Cost: $0.29 M ± 30% | 415472.87 | 2021-02-05
FIS - 11kV feeder FIS7A Exceeding capacity TMU | FIS - Fisherman Island | FIS - Establish a new 11kV feeder - Target Commissioning Dec 2023 - Cost: $0.86 M ± 30% | 415472.87 | 2021-02-05
GYM - 11kV feeder GYM2A Exceeding capacity TMU | GYM - Gympie | GYM - Reconductor GYM2A Mainline - Target Commissioning Jun 2024 - Cost: $0.46 M ± 30%
GYN - 11kV feeder GYN3A Exceeding reliability MSS | GYN - Gympie North | GYN - Improve reliability on GYN3A - Target Commissioning Jun 2023 - Cost: $0.37 M ± 30% | 2829706.3655 | 2021-12-21
KBN - 11kV feeder KBN1B Exceeding reliability MSS | KBN - Karrabin | KBN - Improve reliability on KBN1B - Target Commissioning Jun 2023 - Cost: $0.29 M ± 30%
KCY - 11kV feeder KCY1 Exceeding reliability MSS | KCY - Kilcoy | KCY - Improve reliability on KCY1 - Target Commissioning Dec 2022 - Cost: $0.25 M ± 30%
KCY - 11kV feeders KCY2 & KCY4 Exceeding reliability MSS | KCY - Kilcoy | KCY - Improve reliability on KCY2 & KCY4 - Target Commissioning Aug 2023 - Cost: $0.65 M ± 30% | 1446856.217 | 2021-06-23
KWH - 11kV feeder KWH3 Exceeding reliability MSS | KWH - Kenilworth | KWH - Improve reliability on KWH3 - Target Commissioning Jun 2023 - Cost: $0.36 M ± 30%
MFD - 11kV feeder MFD12A Exceeding capacity TMU | MFD - Morayfield | MFD - Establish a new 11kV feeder - Target Commissioning Nov 2022 - Cost: $1.44 M ± 30% | 885995.4083 | 2021-07-23
MHL - 11kV feeders MHL3A and MHL5A Exceeding capacity TMU | MHL - Mango Hill | MHL - Establish a new 11kV feeder - Target Commissioning Dec 2022 - Cost: $0.79 M ± 30% | 885995.4083 | 2021-07-23
MHL - 11kV feeders MHL2A Exceeding capacity TMU | MHL - Mango Hill | MHL - Establish a new 11kV feeder - Target Commissioning Oct 2024 - Cost: $1.00 M ± 30%
MLB - 11kV feeders MLB13A Exceeding capacity TMU | MLB - Mooloolaba | MLB - Establish a new 11kV feeder - Target Commissioning Oct 2024 - Cost: $1.00 M ± 30%
MSV - 11kV feeder MSV2 Exceeding reliability MSS | MSV - Mt Sylvia | MSV - Improve reliabilty on MSV2 - Target Commissioning Aug 2023 - Cost: $0.29 M ± 30%
MTB - 11kV feeders MTB3A & MTB17A Exceeding reliability MSS | MTB - Mt Tamborine | MTB - Improve reliabilty on MTB3A & MTB17A - Target Commissioning Sep 2023 - Cost: $0.66 M ± 30% | 1014791.777 | 2021-06-23
MTN - 11kV feeder MTNWLP5 Exceeding capacity TMU | MTN - Myrletown | MTN - Estabish a new 11kV feeder - Target Commissioning Dec 2022 - Cost: $0.97 M ± 30% | 1062197.1509 | 2021-08-19
NMC - 11kV feeder NMC15A Exceeding reliability MSS | NMC - North Maclean | NMC - Improve reliabilty on NMC15A - Target Commissioning Nov 2023 - Cost: $0.46 M ± 30%
NSD - 11kV feeders NSD8A & NSD9A Exceeding capacity TMU | NSD - Newstead | NSD - Estabish a new 11kV feeder - Target Commissioning Oct 2023 - Cost: $1.63 M ± 30%
PPE & CMA - 11kV feeders PPE1B, CMA11A & CMA17A Exceeding capacity TMU | PPE - Pimpama East | PPE - Estabish a new 11kV feeder - Target Commissioning Jul 2024 - Cost: $2.00 M ± 30%
PWC - 11kV feeder PWC4 Exceeding capacity TMU & exceeding reliability MSS | PWC - Palmwoods Central | PWC - Capacity & reliability improvement on PWC4 - Target Commissioning Jul 2024 - Cost: $0.46 M ± 30%
RPN - 11kV feeder RPN4A Exceeding capacity TMU | RPN - Redbank Plains | RPN - Estabish a new 11kV feeder - Target Commissioning Aug 2023 - Cost: $1.37 M ± 30% | 1062197.1509 | 2021-08-19
RWD - 11kV feeder RWD1 Exceeding reliability MSS | RWD - Rosewood | RWD - Improve reliabilty on RWD1 - Target Commissioning Sep 2023 - Cost: $0.37 M ± 30%
SFD - 11kV feeder SFD10 Exceeding reliability MSS | SFD - Stafford | SFD - Improve reliabilty on SFD10 - Target Commissioning Sep 2022 - Cost: $0.25 M ± 30% | 1014791.777 | 2021-06-23
SMF - 11kV feeder SMF5A Exceeding reliability MSS | SMF - Samford | SMF - Improve reliability on SMF5A - Target Commissioning Sep 2023 - Cost: $0.32 M ± 30%
TGW - 11kV feeder TGW5 Exceeding reliability MSS | TGW - Toogoolawah | TGW - Improve reliability on TGW5 - Target Commissioning Oct 2022 - Cost: $0.21 M ± 30% | 351072.14 | 2021-03-04
WFD - 11kV feeder WFD1B Exceeding reliability MSS | WFD - Woodford | WFD - Improve reliability on WFD1B - Target Commissioning Jul 2023 - Cost: $0.42 M ± 30%
WHO - 11kV feeder WHO9 Exceeding reliability MSS | WHO - Wivenhoe Dam | WHO - Improve reliability on WHO9 - Target Commissioning Dec 2022 - Cost: $0.14 M ± 30% | 351072.14 | 2021-03-04
WMR - 11kV feeder WMR4 Exceeding reliability MSS | WMR - Wamuran | WMR - Improve reliability on WMR4 - Target Commissioning May 2023 - Cost: $0.36 M ± 30%
WRD - 11kV feeder WRD21A Exceeding reliability MSS | WRD - Wellington Road | WRD - Improve reliability on WRD21A - Target Commissioning Nov 2023 - Cost: $0.40 M ± 30%