## Subs Limits & Committed Solns
Substation Limitations and Committed Solutions
Committed projects have reached design and construction phase, and applicable information is listed below.
Location:
Maps of Energex’s network showing the location of all Energex’s bulk supply and zone substations are presented via the following link:
https://www.energex.com.au/daprmap2022
References:
The Substations Forecast and Capacity Table for a summary of planning information for all Bulk Supply, Zone and Joint owned substations are available in Appendix E of the following hyperlink:
https://www.energex.com.au/about-us/company-information/company-policies-And-reports/distribution-annual-planning-report
Energex Distribution Annual Planning Report is prepared and made available solely for information purposes. While care was taken in the preparation of the information in this report, and it is provided in good faith, Energex accepts no responsibility or liability (including without limitation, liability to any person by reason of negligence or negligent mis-statement) for any loss or damage that may be incurred by any person acting in reliance on this information or assumptions drawn from it, except to the extent that liability under any applicable Queensland or Commonwealth of Australia statute cannot be excluded.
It contains assumptions regarding, among other things, economic growth and load forecasts which may or may not prove to be correct. The forecasts included in the document involve subjective judgements and analysis which are subject to significant uncertainties and contingencies, many of which are out of the control of Energex. Energex makes no representation or warranty as to the accuracy, reliability, completeness or suitability for any particular purpose of the information in this document. All information should be independently investigated, reviewed, analysed and verified, and must not be relied upon in connection with any investment proposal or decision.
All financials presented in this document are correct at the time of writing and represent the existing organisational accounting treatment, which may be subject to change. Energy Queensland is still finalising the alignment of its Cost Allocation Methodology between Ergon and Energex, potentially impacting the treatment of some Capital and Operational Project costs.
Limitation | Impact of limitation on the capacity at trans-dist connection point | Committed solution to address the limitation and alternative options considered
ABM Abermain - Powerlink Secondary System Replacement | Abermain BS - No impact | ABM Abermain - Powerlink Secondary System Replacement - Estimated cost: $1.5M±30% - Estimated commissioning Jun 2022 - No alternative options available | ABM Abermain - Powerlink Secondary System Replacement | ABM Abermain - Powerlink Secondary System Replacement
T16 Nambour - Improve 11kV Backup Protection Reach and Recover TR5/TR7 | Nambour BS - No impact | T16 Nambour - Improve 11kV Backup Protection Reach and Recover TR5/TR7 - Estimated cost: $2.7M ±30% - Estimated commissioning date: Nov 2022 - No alternative options available | T16 Nambour - Improve 11kV Backup Protection Reach and Recover TR5/TR7 | T16 Nambour - Improve 11kV Backup Protection Reach and Recover TR5/TR7
PBH Palm Beach - Replace 33/11kV Transformers | Burleigh Heads BS - No impact | PBH Palm Beach Replace 33/11kV Transformers - Estimated cost: $7.1M ±30% - Estimated commissioning date: Nov 2023 - Alternative options considered: - Replace the existing transformers with 1 x 25MVA transformer and convert the existing 33kV feeder F396 to 11kV to provide a backup supply | PBH Palm Beach Replace 33/11kV Transformers | PBH Palm Beach Replace 33/11kV Transformers
MCE Establish Mount Crosby East Zone Substation | Abermain BS - No impact | MCE Establish Mount Crosby East Zone Substation - Estimated cost: $20.0M ±30% - Estimated commissioning date: June 2024 - No alternative options available | MCE Establish Mount Crosby East Zone Substation | MCE Establish Mount Crosby East Zone Substation
IDY Indooroopilly - Improve 11kV Back-up Protection & Replace 2 x 33kV CBs | Tennyson BS - No impact | IDY Indooroopilly Improve 11kV Back-up Protection & Replace 2 x 33kV CBs - Estimated cost: $3.0M ±30% - Estimated commissioning date: Feb 2023 - No alternative options available | MCE Establish Mount Crosby East Zone Substation | MCE Establish Mount Crosby East Zone Substation
AST Ann Street - Upgrade 110/11/11kV tfmr protection | Charlotte Street ZS & McLachlan Street ZS - No impact | AST Ann Street - Upgrade 110/11/11kV tfmr protection - Estimated cost: $M1.6±30% - Estimated commissioning Dec 2021 - No alternative options available | AST - Upgrade 110/11/11kV tfmr protection | AST - Upgrade 110/11/11kV tfmr protection
CRM Crestmead - Improve 11kV Backup Protection Reach and Replace Protection Relays | Browns Plains BS - No impact | CRM Crestmead - Improve 11kV Backup Protection Reach and Replace Protection Relays - Estimated cost: $1.9M ±30% - Estimated commissioning date: Nov 2022 - No alternative options available
SHW Sherwood - Improve Backup Protection Reach | Tennyson BS - No impact | SHW Sherwood - Improve 11kV Backup Protection Reach & Replace Ageing Relays - Estimated cost: $2.6M ±30% - Estimated commissioning date: Aug 2023 - No alternative options available | QPT Queensport - Improve 11kV Backup Protection Reach | QPT Queensport - Improve 11kV Backup Protection Reach
LBS - Lytton Bulk Supply Improve 11kV Backup Protection Reach | Lytton BS - No impact | LBS Lytton Bulk Supply - Improve 11kV Backup Protection Reach & Replace Ageing Relays - Estimated cost: $2.2M ±30% - Estimated commissioning date: Nov 2022 - No alternative options available | QPT Queensport - Improve 11kV Backup Protection Reach | QPT Queensport - Improve 11kV Backup Protection Reach
LLY - Laidley Improve 11kV Backup Protection Reach | Lockrose BS - No impact | LLY Laidley – Improve 11kV Backup Protection Reach - Estimated cost: $3.0M ±30% - Estimated commissioning date: Feb 2022 - No alternative options available | QPT Queensport - Improve 11kV Backup Protection Reach | QPT Queensport - Improve 11kV Backup Protection Reach
MMC Merrimac - Improve 11kV Backup Protection Reach | Mudgeerba BS - No impact | MMC Merrimac Improve 11kV Backup Protection Reach - Estimated cost: $0.8M ±30% - Estimated commissioning date: Dec 2022 - No alternative options available
ALY Annerley - Improve 11kV Backup Protection Reach | Tennyson BS - No impact | ALY Annerley - Improve 11kV Backup Protection Reach - Estimated cost: $1.3M ±30% - Estimated commissioning date: Mar 2024 - No alternative options available
ARG Acacia Ridge - Replace Relays & Improve 11kV Backup Protection Reach | Algester BS - No impact | ARG Acacia Ridge - Replace Relays & Improve 11kV Backup Protection Reach - Estimated cost: $1.1M ±30% - Estimated commissioning date: Aug 2023 - No alternative options available
MFD Morayfield - Improve 11kV Backup Prot Reach and Replace AB3T19 | Caboolture BS - No impact | MFD Morayfield - Improve 11kV Backup Protection Reach and Replace Motorised Isolator AB3T19 - Estimated cost: $1.1M ±30% - Estimated commissioning date: May 2023 - No alternative options available
WGC Wintergarden Complex - Improve Transformer Low Voltage Backup Protection | Charlotte Street BS - No impact | WGC Wintergarden Complex - Improve Transformer Backup Protection - Estimated cost: $0.5M ±30% - Estimated commissioning date: Mar 2023 - Alternative options considered: Install OC+EF relay for transformer backup protection
NME National Mutual Insurance - Improve Transformer Low Voltage Backup Protection | Charlotte Street BS - No impact | NME National Mutual Insurance - Improve Transformer Backup Protection - Estimated cost: $0.5M ±30% - Estimated commissioning date: Feb 2023 - Alternative options considered: Install OC+EF relay for transformer backup protection
CMB Colonial Mutual Building - Replace Protection Relays | Charlotte Street BS - No impact | CMB Colonial Mutual Building - Improve Transformer Backup Protection - Estimated cost: $0.6M ±30% - Estimated commissioning date: Feb 2023 - No alternative options available
SHN Sheraton Hotel - Replace Protection Relays | Ann Street BS - No impact | SHN Sheraton Hotel - Improve Transformer Backup Protection - Estimated cost: $0.6M ±30% - Estimated commissioning date: Jul 2023 - No alternative options available
BHD Burleigh Heads - Improve Backup Reach & End of Life Relays | Mudgeerba BS - No impact | BHD Burleigh Heads - Improve 11kV Backup Protection reach - Estimated cost: $1.8M ±30% - Estimated commissioning date: Aug 2022 - No alternative options available
AMR Amamoor– Replace 11kV Outdoor Isolators | Gympie BS - No impact | AMR Amamoor– Replace 11kV Outdoor Isolators - Estimated cost: $1,566,098 ±30% - Estimated commissioning date: Mar 2024 - No alternative options available
RIS - Replace Protection Relay | Loganlea BS -No impact | RIS Russell Island - Replace Protection Relay - Estimated cost: $979,082 ±30% - Estimated commissioning: September 2023 - No alternative options available
MLG MLC Building George St | Charlotte St BS -No impact | MLG MLC Building George St - Improve Transformer Backup Protection - Estimated cost: $481,720 ±30% - Estimated commissioning: Feb 2023 - No alternative options available
HIS Hope Island - Replace aging relays & motorised isolator IS3T19 | Coomera BS -No impact | HIS Hope Island - Replace obsolete protection relays, problematic motorised isolator, improve 11kV back-up reach - Estimated cost: $1,479,984 ±30% - Estimated commissioning: Sep 2023 - No alternative options available
COR Replace Protection Relays | Cooroy BS & Gympie BS -No impact | COR Cooran - Improve 11kV backup protection reach & replace problematic relays - Estimated cost: $1,442,078 ±30% - Estimated commissioning: Dec 2023 - No alternative options available
MTB Mt Tamborine - Improve 11kV backup protection reach & replace motorised isolator IS3T19 | Beaudesert BS & Beenleigh BS - No impact | MTB Mt Tamborine - Improve 11kV backup protection reach, replace problematic replace motorised isolator - Estimated cost: $1,549,151 ±30% - Estimated commissioning: Nov 2022 - No alternative options available
GVN Gaven – Improve 11kV Backup Protection & Replace Motorised Isolator | Coomera & Molendinar BS -No impact | GVN Gaven – Improve 11kV Backup Protection & Replace Motorised Isolator - Estimated cost: $1,768,308 ±30% - Estimated commissioning: Jan 2023 - No alternative options available
FDS Flinders Replace 11kV & 33kV outdoor isolators | Raceview BS - No impact | FDS Flinders Zone Substation – Replace 33kV and 11kV outdoor isolators - Estimated cost: $1,470,760 ±30% - Estimated commissioning: May 2023 - No alternative options available
QEE MacArthur Central Plaza – Replace Protection Relays & Establish Transformer Backup Protection | Charlotte St BS -No impact | QEE MacArthur Central Plaza – Replace Protection Relays & Establish Transformer Backup Protection - Estimated cost: $627,602 ±30% - Estimated commissioning: Aug 2023 - No alternative options available
GBS Gatton Bulk Supply - Replace Protection Relays | Gatton BS -No impact | GBS Gatton Bulk Supply - Replace Protection Relays - Estimated cost: $835,262 ±30% - Estimated commissioning: Mar 2023 - No alternative options available
CTG Casino Towers George St - Replace Protection Relays | Charlotte St BS -No impact | CTG Casino Towers George St – Replace Protection Relays - Estimated cost: $627,602 ±30% - Estimated commissioning: Aug 2023 - No alternative options available
BRD Brendale Replace Protection Relays | Brendale BS -No impact | BRD Brendale - Replace Protection Relays - Estimated cost: $958,409 ±30% - Estimated commissioning: Mar 2023 - No alternative options available
BLB Bulimba - Improve BU Reach, Replace Relays & 33kV Disconnectors | Queensport BS -No impact | BLB Bullimba -Improve backup Protection Reach, Replace Relays & 33kV Disconnectors - Estimated cost: $1,883,026 ±30% - Estimated commissioning: June 2023 - No alternative options available
HIL Hayes Inlet Replace Age 33kV VTs & Relays | Hays Inlat BS -No impact | HIL Hays Inlat -Improve backup Protection Reach, Replace Relays & 33kV Disconnectors - Estimated cost: $496,615 ±30% - Estimated commissioning: June 2023 - No alternative options available
TGW Toogoolawa - Improve 11kV Backup Protection Reach | Sunrise Hills BS -No impact | TGW Toogoolawa - Improve 11kV Backup Protection Reach - Estimated cost: $413,438 ±30% - Estimated commissioning: Oct 2022 - No alternative options available
NRA Narangba - Improve Backup Protection Reach | Hays Inlet BS -No impact | NRA Narangba - Improve Backup Protection Reach - Estimated cost: $1,776,192 ±30% - Estimated commissioning: May 2023 - No alternative options available
AHD Alexandra Headland – Replace Protection Relays | Palmwoods BS -No impact | AHD Alexandra Headland – Replace Protection Relays - Estimated cost: $1,265,379 ±30% - Estimated commissioning: Apr 2023 - No alternative options available
BPN Browns Plains - Replace Protection Relays & SACS | Browns Plains BS -No impact | BPN - Replace Protection Relays - Estimated cost: $1,019,410 ±30% - Estimated commissioning: May 2023 - No alternative options available
NGE Nudgee - Replace 11kV switchgear | Nudgee BS - No impact | NGE Nudgee - Replace 11kV Switchgear - Estimated cost: $10,554,528 ±30% - Estimated commissioning date: Apr 2024 - No alternative options available
BBH - Replace Protection Relays | Mudgeeraba BS -No impact | BBH Broad Beach - Replace Protection Relays - Estimated cost: $1,648,039 ±30% - Estimated commissioning: Oct 2023 - No alternative options available
BDS Beaudesert - Replace Protection Relay | Beaudesert BS -No impact | BDS Beaudesert - Replace Protection Relays - Estimated cost: $2,031,064 ±30% - Estimated commissioning: Nov 2023 - No alternative options available
SIS Stradbroke Island Replace 33/11kV TR3, 33kV Bus and CB3T32 | Beenleigh BS - No impact | SIS Stradbroke Island - Replace 33/11kV TR3, CB3T32 and 33kV bus - Estimated cost: $7,926,252 ±30% - Estimated commissioning: Apr 2024 - No alternative options available
DBS - Doboy Bulk Supply Improve 11kV Backup Protection Reach | Doboy BS -No impact | SSDBS - Doboy Bulk Supply Improve 11kV Backup Protection Reach - Estimated cost: $909,989 ±30% - Estimated commissioning: June 2023 - No alternative options available
VPK Victoria Park - Replace Protection Relay | Victoria Park BS -No impact | SSVPK Victoria Park - Replace Protection Relays - Estimated cost: $1,127,097 ±30% - Estimated commissioning: Oct 2023 - No alternative options available
MHS Mineral House- Improve Transformer Backup Protection | Charlotte St BS -No impact | MHS Mineral House - Improve Transformer Backup Protection - Estimated cost: $403,936 ±30% - Estimated commissioning: Jan 2024 - No alternative options available
T11 Caboolture Bulk Supply - Replace Ageing Relays & Establish 110KV Feeder POPS | Caboolture BS -No impact | T11 Caboolture Bulk Supply - Replace Ageing Relays & Establish 110KV Feeder POPS - Estimated cost: $380,501 ±30% - Estimated commissioning: June 2023 - No alternative options available
CST Charlotte Street - SACS Upgrade & replace DUOBIAS | Murarrie BS -No impact | CST Charlotte Street – Upgrade 110kV Feeder Protection and Replace Duobias Relays - Estimated cost: $2,739,450 ±30% - Estimated commissioning: Apr 2024 - No alternative options available
SPD Surfers Paradise – Improve Back-up Protection Reach & Replace Obsolete Relays | Merrimac BS & Molendinar BS -No impact | SPD Surfers Paradise - Improve Back-up Protection Reach & Replace Obsolete Relays - Estimated cost: $2,903,189 ±30% - Estimated commissioning: May 2024 - No alternative options available
BVL Booval - Improve Back-up Protection Reach | Raceview BS -No impact | BVL Booval - Improve Back-up Protection Reach - Estimated cost: $701,209 ±30% - Estimated commissioning: Jul 2023 - No alternative options available
NGE Nudgee- Replace 4 x 110kV CBs | Nudgee BS -No impact | NGE Nudgee - Replace 145kV circuit breakers, 145kV current transformers, 33kV voltage transformer, obsolete protection relays - Estimated cost: $3,209,477 ±30% - Estimated commissioning: Dec 2024 - No alternative options available
ACR Albany Creek - Replace 6 x 11kV CB's & 2 x 11kV Relays | Brendale BS -No impact | ACR Albany Creek - Replace problematic 12kV circuit breakers, obsolete protection schemes, obsolete protection relays - Estimated cost: $1,658,445 ±30% - Estimated commissioning: Dec 2023 - No alternative options available
PGN Peregian - Replace KBCH Relays | Sunrise Hills BS -No impact | PGN Peregian - Replace KBCH Relays - Estimated cost: $1,092,981 ±30% - Estimated commissioning: June 2023 - No alternative options available
TMH - Replace motorised isolator IS3T19 | Loganlea BS -No impact | TMH - Replace motorised isolator, obsolete protection relays, improve feeder protection selectivity - Estimated cost: $1,742,393 ±30% - Estimated commissioning: Oct 2023 - No alternative options available
LGL - Improve 11kV Backup Protection | Loganlea BS -No impact | LGL Loganlea - Improve 11kV Backup Protection & Replace Obsolete Relays - Estimated cost: $1,040,999 ±30% - Estimated commissioning: Dec 2023 - No alternative options available
MRB Recover 33kV and 11kV Outdoor Isolators | Lockrose BS - No impact | MRB Murrumba Zone Substation – Recover 33kV and 11kV outdoor isolators - Estimated cost: $3,744,124 ±30% - Estimated commissioning: Mar 2024 - No alternative options available
GLY - Improve 11kV Backup Protection | Stafford BS / Brendale BS -No impact | GLY Grovely - Improve 11kV Backup Protection - Estimated cost: $2,988,165 ±30% - Estimated commissioning: Oct 2023 - No alternative options available
SPF - Improve 11kV Backup Protection and Replace Obsolete Relays | Goodna BS - No impact | SPF Springfield & STC Springfield Town Centre - Improve 11kV Backup Protection & Replace Obsolete Relays - Estimated cost: $1,598,809 ±30% - Estimated commissioning: Dec 2023 - No alternative options available
CRB - Improve 11kV Backup Protection | Burleigh Heads BS - No impact | CRB Currumbin - Improve 11kV Backup Protection - Estimated cost: $1,069,564 ±30% - Estimated commissioning: Nov 2023 - No alternative options available
SPO – Improve Back-up Protection Reach & Upgrade Protection Scheme | Merrimac BS & Molendinar BS -No impact | SPO South Port - Improve Back-up Protection Reach & Upgrade Protection Scheme - Estimated cost: $2.5m ±30% - Estimated commissioning: Aug 2023 - No alternative options available
BDA – Improve Back-up Protection Reach & Upgrade Protection Scheme | Tennyson BS - No impact | BDA Burranda - Improve Back-up Protection Reach & Upgrade Protection Scheme - Estimated cost: $951,576m ±30% - Estimated commissioning: June 2024 - No alternative options available
CNB - Improve Backup Protection Reach and Upgrade TR DIFF Scheme | Beenleigh BS - No impact | CNB Connubia - Improve Backup Protection Reach and Upgrade TR DIFF Scheme - Estimated cost: $1,499,167 ±30% - Estimated commissioning: Jan 2024 - No alternative options available
CPS - Improve 11kV Backup Protection Reach | Cleveland BS -No impact | CPS Capalaba South - Improve 11kV Backup Protection Reach - Estimated cost: $940,113 ±30% - Estimated commissioning: Sep 2023 - No alternative options available
SRD Scrub Road - SACS Upgrade | Belmont BS - No impact | SRD Scrub Road – Improve Backup Protection Reach and Upgrade SACS - Estimated cost: $872,243 ±30% - Estimated commissioning: December 2022 - No alternative options available
SMF - Samford Improve 11kV Backup Protection Reach | Brendale BS - No impact | SMF Samford – Improve 11kV Backup Protection Reach, & Replace Ageing Protection Relays & 33kV Motorised Isolator - Estimated cost: $1,927,646 ±30% - Estimated commissioning: June 2024 - No alternative options available
TWG - Replace 33kV OD isolators | T30 Ashgrove West BS - No impact | TWG Toowong - Replace 33kV OD isolators - Estimated cost: $1,414,424 ±30% - Estimated commissioning: March 2024 - No alternative options available
YDA - Yandina Replace KBCH and Duobias Relays | Nambour BS -No impact | YDA Yandina - Upgrade TR DIFF Scheme and Replace Protection Relays - Estimated cost: $1,371,445 ±30% - Estimated commissioning: Dec 2023 - No alternative options available
GNA - Replace DUOBIAS/Argus 1 Relays | H38 Goodna BS -No impact | GNA Goodna - Replace DUOBIAS/Argus 1 Relays - Estimated cost: $1,786,563 ±30% - Estimated commissioning: July 2024 - No alternative options available
CCY Upgrade AFLC unit | Cades County BS - No impact | CCY Cades County – Replace Station Services Transformers, Replace Problematic Relays & Rectify Capacitor Banks - Estimated cost: $1,647,798 ±30% - Estimated commissioning: August 2023 - No alternative options available
NSD - Replace Argus 1 Relays | Murarrie BS - No impact | NSD Newstead & SSCGT- Replace Protection Relays - Estimated cost: $1,543,629 ±30% - Estimated commissioning: March 2024
ENG Improve 11kV Backup Protection Reach | Stafford BS - No impact | ENG Eneggora - Improve 11kV Backup Protection Reach - Estimated cost: $1,017,203 ±30% - Estimated commissioning: June 2024
ABY - Replace KBCH120 on TR1 & SACS Upgrade | Abermain BS - No impact | ABY Amberley – Replace KBCH120 on TR1 and Improve Backup Protection Reach - Estimated cost: $1,229,938 ±30% - Estimated commissioning: August 2024 - No alternative options available
YMT - Replace KBCH and DUOBIAS Relays | Raceview BS - No impact | YMT Yamanto – Replace Problematic Relays and Improve 11kV Backup Protection - Estimated cost: $1,559,585 ±30% - Estimated commissioning: June 2024 - No alternative options available
MHL - Improve 11kV Backup Reach & Replace IS3T19 | GFN Griffin BS / HIL Hayes Inlet BS - No impact | MHL Mango Hill - Improve 11kV Backup Reach & Repalce IS3T19 - Estimated cost: $1,744,924 ±30% - Estimated commissioning: July 2024 - No alternative options available
STT - Improve 11kV BackUp Protection | T108 Beenleigh BS - No impact | STT Stapylton - Improve 11kV Backup Prot - Estimated cost: $1,002,589 ±30% - Estimated commissioning: May 2024 - No alternative options available
YTA Yatala - Replace Motorised Isolator IS3T29 | T108 Beenleigh BS - No impact | YTA Yatala - Replace motorised isolator IS3T29 - Estimated cost: $1,051,706 ±30% - Estimated commissioning: April 2024 - No alternative options available
RLA Rocklea - Improve 11kV Backup Reach and Replace Relays | Archerfield BS - No impact | RLA Rocklea - Improve 11kV backup protection reach and replace protection relays - Estimated cost: $492,542 ±30% - Estimated commissioning: May 2024 - No alternative options available
CHL Camp Hill - Improve 11kV Backup Protection | Coorparoo BS - No impact | CHL Camp Hill - Improve 11kV Backup Protection - Estimated cost: $1,154,963 ±30% - Estimated commissioning: Oct 2024 - No alternative options available
MLS Mclachlan Street - Replace Problematic Relays & SACS Upgrade | T30 Ashgrove West BS - No impact | MLS Mclachlan Street - Replace problematic relays & SACS upgrade - Estimated cost: $666,063 ±30% - Estimated commissioning: December 2024 - No alternative options available
IPL Innisplain - Improve 11kV Backup Protection | Beaudesert BS - No impact | IPL Innisplain - Improve 11kV Backup Protection - Estimated cost: $51,639 ±30% - Estimated commissioning: June 2024 - No alternative options available
IPS Ipswich South - Improve 11kV Backup Protection Reach | Raceview BS - No impact | IPS Ipswich South – Improve 11kV Backup Protection Reach & Replace Argus 1 Relays - Estimated cost: $1,301,675 ±30% - Estimated commissioning: February 2024 - No alternative options available
BRT Brighton - Improve 11kV backup protection reach | Sandgate BS - No impact | BRT Brighton - Improve 11kV backup protection reach - Estimated cost: $1,032,506 ±30% - Estimated commissioning: June 2024 - No alternative options available
BIS Bribie Island - Improve 11kV Backup Protection Reach | Caboolture BS - No impact | BIS Bribe Island - Improve 11kV Backup Protection Reach - Estimated cost: $957,933 ±30% - Estimated commissioning: June 2024 - No alternative options available
VAR - Transformer Bunding Priority P0 & P1 | Various BS - No impact | VAR Various - Transformer Bunding Priority P0 & P1 - Estimated cost: $2,131,194 ±30% - Estimated commissioning: Mar 2024 - No alternative options available
DBY Deception Bay Install POPS Scheme | Hays Inlet BS - No impact | SSDBY Deception Bay - Install POPS Scheme - Estimated cost: $117,536 ±30% - Estimated commissioning: Mar 2024 - No alternative options available
KRN Kedron - Replace 33kV OD Isolators | Stafford BS - No impact | KRN Kedron - Replace 33kV OD isolators - Estimated cost: $1,640,123 ±30% - Estimated commissioning: September 2024 - No alternative options available
RWD Rosewood - Rebuild Substation to Replace Ageing Assets | Abermain BS - No impact | RWD Rosewood - Rebuild Substation to Replace Ageing Assets - Estimated cost: $10,926,900 ±30% - Estimated commissioning: June 2026 - No alternative options available
WED West End – Replace 11kV Switchgear | Rocklea BS - No impact | WED West End – Replace 11kV Switchgear - Estimated cost: $5,768,404 ±30% - Estimated commissioning: February 2026 - No alternative options available
ESK - Impr 11kV Backup Prot Reach | Lockrose BS - No impact | ESK Esk - Impr 11kV Backup Prot Reach - Estimated cost: $1,452,433 ±30% - Estimated commissioning: June 2024 - No alternative options available
UMG Upper Mt Gravatt - Replace motorised isolator IS3T19 | Belmont BS - No impact | UMG Upper Mt Gravatt - Replace motorised isolator IS3T19 - Estimated cost: $1,366,343 ±30% - Estimated commissioning: October 2024 - No alternative options available
HPK Holland Park - Replace 33/11kV Transformer TR2 | Coorparoo BS - No impact | HPK Holland Park - Replace 33/11kV Transformer TR2 - Estimated cost: $5,245,528 ±30% - Estimated commissioning: December 2024 - No alternative options available